## Sheet1
2012 - 2016 Nebraska Supreme Court Technology Strategic Plan - Goals and Objectives
Goal # | Goal Descriptions | 2013 Benchmarks for Success | 2014 Benchmarks for Success | 2016 Benchmarks for Success | August 2015 | Midpoint Review
Goal # |  | 1 Year | 2 Year | 5 Year
5.1 | Technologies - Nebraska's courts will have equal distribution of technology and bandwidth across all courts. Equal distribution of technology and bandwidth will all Nebraska's court system to provide a better experience for all citizens of Nebraska. |  |  |  |  | Recommendation
5.1.1 | Use video conferencing statewide for remote appearances and virtual attendance in court proceedings. | Making this service available to all County Courts Clerk Magistrates. Marketing the availability of this service to all the Clerks of the District Courts. Having 33% of County Courts using this service in a court proceeding. Having 20% of district Courts using this service in a court proceeding. Communicating with the Nebraska State Bar Association of the availability of this service. Piloting the use of this service with practicing attorneys and firms with trial courts. | Having 67% of County Courts utilizing this service. Having 50% of District Courts utilizing this service. | Having all County Courts utilizing this service. Having all District Courts utilizing this service. | Current count of JABBER accounts: 90 County Courts, 40 District Courts, 18 Correctional facilities/law enforcement offices, 33 Probation/Drug court personnel, 21 Interpreters, 31 Attorneys, 8 Mediation users. Meeting with NSBA to discuss what opportunities could be opened up if JABBER accounts were offered as part of their membership. | Updated - New benchmarks.
| 5.1.1.1 | Midpoint Strategic Plan Review and Evalution: The benchmarks for the objective in 5.1.1 have been fulfilled and new benchmarks are being defined for the the 2014-2016 period. Objectives 5.1.6 and 5.3.4 will be rolled into this objective. |  | Have 90% of County Courts and 66% of District Courts utilizing this service. |  | New.
5.1.2 | Implement electronic Appellate Courts records. | Having all District Courts utilizing the Electronic Docketing application. Having all cases using imaging for document storage. Making electronic filing available for attorneys for filing briefs and motions. Exploring the use of electronic filing with the State Attorney General's Office, County Public Defenders and the Commission on Public Advocacy. | Having 50% of all case filings electronically including motions, briefs and Bill of Exceptions. | Having 90% of all case filings electronically including motions, briefs and Bill of Exceptions. | Efiling rules approved by the Court. Testing of new online case search system in progress. | Updated.
5.1.3 | Allow for simultaneous language translation service (Interpreter of video and audio recordings. | Researching what other states are doing with regard to this issue. | Implement a pilot project using the technology and reporting of the progress to the Technology Committee. |  | Referral to Interpreter Advisory Committee | Updated.
5.1.4 | Create a paperless and secure information process for the Judicial Nomination Committee and for the Judicial Qualification Committee. | Studying the use of this electronic process for the Judicial Qualification Committee. Utilizing password protected portable document filing (PDF) format for all correspondence for both committees. |  |  | This objective has been completed and is in use as of July 2012. | Updated/Complete.
5.1.5 | Study the potential transitions from paper to electronic publication of the Appellate Courts opinions. | Researching what other states have done in this area. Working with the Reporter's Office to evaluate potential options for the subscriber based web services and to consider joint recommendation to the Court. | Finding a process to transition from paper to electronic publishing. | Have a process in place for paperless publication of opinons. | A prototype of a web application for an online library of opinions was created by Nebraska.gov. Finalizing functional specifications behind electronic publication process. Contract with Hein to scan old bound volumes under final review. | Updated.
5.1.6 | Provide proactive coordination of video conferencing services. | Working with the Office of the CIO to coordinate video conferencing. Conducting a survey of video conferencing users to measure their satisfaction with using the service. |  |  | JUSTICE BA's and new IT Systems Support Specialists can set up new user accounts and assist current users with video conferencing services. All courts have the ability to take advantage of video conferencing. | Updated - New benchmarks.
| 5.1.6.1 | Midpoint Strategic Plan Review and Evalution: Rolled into objective 5.1.1 | Determine the methods being pursued by entities outside of the courts, i.e. attorneys, Dept. of Corrections; to connect through remote video conferencing. | Any courtroom equipped for remote appearances should be able to connect to attorneys' systems, corrections systems, interpreter systems and law enforcement systems. |  | New
5.1.7 | Create My Cases page subscription service through Nebraska.gov. | Working with Nebraska.gov to develop this service. | Creating a pilot phase to allow Nebraska attorneys to use the service. Surveying the users to measure their satisfaction of the service. | Having full implementation of the application. | Nebraska.gov could create something but requirements would have to be defined. - There is no work currently being done on this objective. | Updated - New benchmarks.
| 5.1.7.1 | Midpoint Strategic Plan Review and Evalution: New benchmarks are being defined for the the 2014-2016 period. | Planning with Nebraska.gov to integrate into eFiling | Fully implemented as a part of the attorney eFiling dashboard |  | New
5.1.8 | Ensure fast communication network bandwidth is available to all courthouses. | Ensuring all Nebraska Courthouses have a minimum of 768Kbps upload connectivity and 1.0 Mbps download connectivity from the State Data Communications Network. Receiving daily usage reports from the Office of the CIO measuring the bandwidth usage at each Courthouse. | Continuing to investigate and monitor the network to ensure a good user experience for data and video connectivity. | Continuing to investigate and monitor the network to ensure a good user experience for data and video connectivity. | Coordination with OCIO networking services to improve connectivity at courthouses is a continual process. With new providers and infrastructure upgrades across the state, options and speeds continue to improve and costs are driven down. Under current contracts no courthouse has less than 1M down/896 K up (majority of courthouse bw connections are much higher). | Updated.
5.2 | Standards - Through the use of standards Nebraska courts will make every effort for the uniform collection of information. |  |  |  |  | Recommendation
5.2.1 | Develop a technical business plan for all court publications. | Working with the Administrative Office of the Courts Public Information Officer and the Office of the Reporter of Decisions and other stakeholders to develop a technical business plan. Working with third party developers to develop the technical business plan for court publications. Researching other states to find out how they are implementing technical business plans for their court publications. | Working with the Administrative Office of the Courts Public Information Officer and the Office of the Reporter of Decisions and other stakeholders to implement the technical business plan. Working with third party developers to implement the technical business plan for court publications. | Assuring that all court and probation publications are centralized, indexed and searchable for public access electronically. | Falls under work in progress by the Courts Public Information Officer in coordination with the Probation Division. | Updated.
5.2.2 | Create common technology court rules for the use of email addresses and texting in JUSTICE. | Developing party email address and telephone number fields in the JUSTICE Case and Financial Management System for use in notifying parties of court proceedings, hearing dates and time payment notices. Providing fields in JUSTICE for email addresses and telephone numbers that are only available to Judges and court staff. | Implementing the application in 100% of the trial courts. Producing reports in JUSTICE that will track the use of this technology to produce increased staff productivity and postage savings for county governments. | Continue to measure usage and implementation. | This objective has been completed and is in use as of July 2012. | Updated/Complete.
5.2.3 | Create a catalog of forms for District Court judges in JUSTICE. | Completing research of forms for District Court Judges. | Implementing the availability of District Court forms in JUSTICE. | Integrate forms with modern judges' interface to JUSTICE | No work is currently being performed on this objective. | Updated.
5.2.4 | Provide speech recognition software for all County Court transcribers. | Researching the availability of speech recognition software (Dragon Naturally Speaking and others); test the software for implementation by transcribers. This would be software similar to real-time reporting software. | Completing a demonstration project of this application. | Mandating the use of speech recognition software by court transcribers and outsourced court transcribers. | Transcription for county courts is being outsourced and there is no need for the branch to provide speech recognition softwared. | Updated/Complete.
5.3 | Jurisdictional Boundaries - Nebraska courts will use technology to identify and respond to trends that are challenging today's traditional jurisdictional boundaries, recognizing these efforts must consider existing laws, court rules and professional ethics. |  |  |  |  | Recommendation
5.3.1 | Develop proposed rules for electronic devices in courtrooms. | Developing proposed rules for electronic devices in courtrooms, including attorneys, parties and observers in the courtroom. | Recommending the review or adoption of the proposed rules by the Nebraska Supreme Court. | Reviewing the rules for updates or use of new technology. | Policy is being set at the local/district level. | Updated/Complete.
5.3.2 | Allow interconnection of personal and work devices for email and network access. | Working with the Office of the CIO to follow the best business practice for allowing interconnection of personal devices to the State Data Communications Network. Alerting judges and court staff as to how the process works. Developing proposed rules for implementation within the Judicial Branch. |  |  | The branch is following the Nebraska Information Technology Commission (NITC) standard policy for allowing connection to state email on a personal device. Options for VPN and Remote desktop are also available. | Updated/Complete.
5.3.3 | Assist trial courts with development of wireless public Internet access in Courthouses. | Working with local courts to effectively install and use wireless public Internet access in 10% of local courts. | Working with local courts to effectively install and use wireless public Internet access in 50% of local courts. | Working with local courts to effectively install and use wireless public Internet access in 100% of local courts. | Court technology standards will reflect providing public wireless internet access as a best practice, but cost must be covered by the county. | Updated - New benchmarks.
| 5.3.3.1 | Midpoint Strategic Plan Review and Evalution: The benchmarks for the objective in 5.3.3 have been revised as is may not be economical for all courthouses to pay for public Wi-Fi |  | Working with local courts to effectively install and use wireless public Internet access in 85% of local courts. |  | New.
5.3.4 | Assist trial courts with the installation and use of MOVI/Jabber video conferencing services. | Having 100% of County Courts with MOVI/Jabber accounts and 50% of County Judges registered to use MOVI/Jabber accounts. | Having 50% of District Courts with MOVI/Jabber accounts and 25% of District Judges registered to use MOVI/Jabber accounts. | Having all trial courts with MOVI/Jabber accounts and all trial court judges registered to use MOVI/Jabber accounts. | Same as 5.1.1 and 5.1.6 | Updated - New benchmarks.
| 5.3.4.1 | Midpoint Strategic Plan Review and Evalution: Rolled into objection 5.1.1 | Determine the methods being pursued by entities outside of the courts, i.e. attorneys, Dept. of Corrections; to connect through remote video conferencing. | Any courtroom equipped for remote appearances should be able to connect to attorneys' systems, corrections systems, interpreter systems and law enforcement systems. |  | Updated.
5.3.5 | Use social media (Twitter, Facebook, and others) to market court services. | Researching how other states are using social media to market court services and report to the Technology Committee. | Attempting small pilot projects around the State using social media. | Creating a permanent project statewide. | Starting a pilot project to have Drupal send judicial branch press release information through a Twitter account. | Updated.
5.3.6 | Allow for working sharing using electronic access between the Clerks of the District Courts and Clerk Magistrates and working with the Court Reengineering Committee to implement this objective. | Implementing a pilot project with a County Court and a District Court. Measuring the feedback from the pilot project to determine what worked and what did not work. Working with Trial Court Services Director for possible changes to the work sharing process. | Adding additional courts to the project. |  | There are no remaining technological barriers to collaboration between Clerk Magistrates and Clerks of the District court. Electronic tools are available to aid in all aspects of work sharing. | Updated/Complete.
5.4 | Technology Rules and Statutes - Nebraska courts will proactively explore and update rules or be useful in working with technology issues. |  |  |  |  | Recommendation
5.4.1 | Identify statutory impediments to electronic transferring of cases in trial courts. | Reviewing potential legislation and identifying additional legislation that may be adopted to enact this objective. | Continuing to monitor the legislative process for achieving this objective. |  | Review of statutory impediments should be performed as a part of overall review of impediments to electronic case mangagement. (See also Objective 5.5.5) | Updated.
5.4.2 | Create demand for additional bench use of the JUSTICE Case Management System. | Developing a plan to implement the use of JUSTICE from the Bench for all Districts Courts, County Courts and Separate Juvenile Courts. Building useful applications for judges to use from the Bench. | Having JUSTICE applications in place for judges to use from the Bench. | Having 95% of trial court judges using JUSTICE from the Bench. | This objective will be completed with the implementation of a Judges' Portal to JUSTICE. | Updated - New benchmarks.
| 5.4.2.1 | Midpoint Strategic Plan Review and Evalution: New benchmarks are being defined for the the 2014-2016 period. | Having a timeline for development and implementation of a Judges' Portal to JUSTICE. | 95% of judges using the new portal for case management in JUSTICE |  | New.
5.5 | JUSTICE - Nebraska courts will develop a long term plan for JUSTICE Case and Financial Management System. Develop and enhance the JUSTICE Court Case scheduling system that interacts with handheld devices. |  |  |  |  | Recommendation
5.5.1 | Electronic filing on all Criminal, Traffic cases, all case subtypes in all courts. | Having electronic filing on all Criminal, Traffic cases through JUSTICE. | Having electronic filing available on all case subtypes in JUSTICE. |  | Small claims statute changes were not approved by the legislature. New DC filing types are being added for subsequent case filing. Piloting a new web service for criminal new case and subsequent case filing by county attorneys and public defenders directly from CMS. | Updated - New benchmarks.
| 5.5.1.1 | Midpoint Strategic Plan Review and Evalution: New benchmarks are being defined for the the 2014-2016 period. | Identify all the remaining subtypes not yet available for eFiling | Integrate the remaining case subtypes into eFiling |  | New.
5.5.2 | Develop and utilize Juvenile PDF orders for all case types. | Working with the JUSTICE Juvenile Automation Committee to develop the prototype Juvenile PDF Order and then coding and testing the prototype on JUSTICE. |  |  | Journal Entry and Order for both the Offender and the 3A Juvenile dockets are being generated by JUSTICE in production. | Updated/Complete.
5.5.3 | Develop an attorney contact database with multiple email and physical addresses. | Researching the possibility of using the Nebraska State Bar Association's existing attorney database to interface with JUSTICE. | Informing attorneys how the database and data will work in JUSTICE. Launching the application statewide. |  | eNotice effective in 2015. The trial courts will centralize to a master file of attorney names, bar numbers and email addresses, and new attorney information will be received electronically from Judicial Branch Attorney Services. Attorneys will manage their email addresses centrally via the online eFiling portal | Updated/Complete.
5.5.4 | Use electronic filing and management for electronic exhibits. | Researching other states to find out how they solved this issue. Locating additional resources to assist in identifying solutions for this objective. | Developing rules for managing and handling electronic exhibits. | Implementing and adopting rules for this issue. | Technology Committee will designate resources to review the Supreme Court rules relevant to this objective. | Updated
5.5.5 | Move to a paperless based court case management system. | Creating standards and procedures to achieve this objective. | Adopting rules to achieve this objective. | Fully implementing this objective on a state-wide basis. | Technology Committee will designate resources to evaluate the best method of fully researching all the statutory impediments, as well as policy questions of document signature, transfer and storage. | Updated
5.5.6 | Create a full JUSTICE case management system application for downloading of pleadings through a subscription based service. | Researching how this objective can be accomplished. | Developing a business plan to implement this objective. | Fully implementing this objective on a state-wide basis. | Currently there is no work being performed on this objective. | Updated - New benchmarks.
| 5.5.6.1 | Midpoint Strategic Plan Review and Evalution: Split and rolled into objectives 5.1.7 (for attorneys) and objective 5.4.2 (judges) | 5.1.7 - Planning with Nebraska.gov to integrate into eFiling 5.4.2 - Having a timeline for development and implementation of a Judges' Portal to JUSTICE | 5.1.7 - Fully implemented as a part of the attorney eFiling dashboard 5.4.2 - 95% of judges using the new portal for case management in JUSTICE |  | New
5.5.7 | Create an application that electronically transfers the records of a case from County to County. | Developing standards and practices to accomplish this objective. | 2014 benchmark pushed to 2016 | Fully implementing this objective on a state-wide basis. | Objective milestone will be pushed out to 2016 | Updated - New benchmarks.
5.6 | Date Collection and Sharing |  |  |  |  | Recommendation
5.6.1 | Allow electronic access to trial court opinions statewide. | Researching how this is done in other states, how decisions are posted, emails, are the processes automated and are they integrated with court marketing channels. | Developing a pilot project with a small number of courts involved. Surveying potential users of the system to identify their needs. Expanding the number of participating courts. Having JUSTICE post a flag to display the opinion electronically on the Court's web site including a searchable feature. | Implementing on a state-wide basis. | A vendor would need to supply the front-end for a search of court designated opinions. Vendor options could include Nebraska.gov or other attorney services-focused providers. | Updated
5.6.2 | Have District Court judges maintain district wide calendars with electronic access to all cases. | Redesign the Calendar application in JUSTICE to allow for increased user friendliness and a feature rich product. | Having all District Courts utilizing JUSTICE Calendar applications. Working with Nebraska.gov to allow for public internet access to all court calendars. |  | Exploring options for a judges' portal to include a calendaring application that integrates with JUSTICE and that interfaces for court staff, attorneys and judges. | Updated - New benchmarks.
| 5.6.2.1 | Midpoint Strategic Plan Review and Evalution: New benchmarks are being defined for the the 2014-2016 period. | JUSTICE calendaring capabilities cannot be upgraded adequately to support all the needs identified for sharing and group calendar access. | Identify new calendaring tools for judges - desktop vs. portal |  | New.